## 25S1
ID | Decision Field | Decision | Description of decision and impact | Source | Owner | Stakeholders | Importance | Urgency | Status | Decision Date | Due Date | Record of decision made
| 1-Administration & Management, 2-Website, 3-Social Media | [5 empty] | Relative Importance: 1-High, 2-Medium, 3-Low | Relative Urgency: 1-High, 2-Medium, 3-Low | Status of item: 1-Not started, 2-In progress, 3-Complete | The date that the decision is made | The date that the decided item is due
1 | 1 | Rename the team | Due to the reconstruction of the project, our team is now named as the AmplifyAI team. | Client meeting | All AmplifyAI Team Members | The AmplifyAI Team, Tutor/Examiner, Client | 2 | 1 | 3 | 14/03/2025 | 14/03/2025
2 | 1 | Create the Github repository | We decided to create a new Github repository under the SouthernCross AI organisation. | Team meeting | All AmplifyAI Team Members | The AmplifyAI Team, Tutor/Examiner, Client | 1 | 1 | 3 | 14/03/2025 | 21/03/2025 | GitHub Page url: https://github.com/southern-cross-ai/AmplifyAI/tree/main
3 | 1 | Draft Statement of Work | We decided to draft the Statement of Work based on the new AmplifyAI work. | Team meeting | Xuefei Luan | The AmplifyAI Team, Tutor/Examiner, Client | 1 | 2 | 2 | 14/03/2025 | 28/03/2025 | Statement of Work url: https://docs.google.com/document/d/1eq5HK3yWepCNZTHTYuJw4xL2f_AI02uAox3tydKgKr4/edit?tab=t.0#heading=h.wsclr25zt1ot
4 | 2 | Construct the skeleton of the Southern Cross AI website | We decided to design and develop the skeleton of the Southern Cross AI website for future polishing and contents. The website will be based on html/css/javascript. | Team meeting | Xiangyu Bi, Wenzhao Zheng, Xinyi Chen, Yuetao Zhang, Ke Wen, Yuhang Chen | The AmplifyAI Team, Tutor/Examiner, Client | 1 | 1 | 3 | 14/03/2025 | 28/03/2025 | Discussion made and outcome is shown in decision #6
5 | 1 | Establish the project management tools | As advised by the tutors, we decided to use backlog, milestone, roadmap and burn down chart for project management. | Client meeting, Tutor meeting, Team meeting | Xuefei Luan | The AmplifyAI Team Tutor/Examiner | 1 | 1 | 3 | 14/03/2025 | 28/03/2025 | Xuefei Luan is responsible for establishing the backlog, milestone and roadmap of Github. All others are responsible to assigning and reporting issues related to their tasks.
6 | 3 | Initialise official accounts of social media | As advised by the clients, we decided to sign up official accounts of 6 social media and link them to Metricool. We will send one post per social media to test the availability. | Team meeting | All AmplifyAI Team Members | The AmplifyAI Team, Client | 1 | 1 | 3 | 14/03/2025 | 28/03/2025 | Instegram: https://www.instagram.com/southerncross.ai Thread: https://www.threads.net/@southerncross.ai X (Twitter): https://x.com/AiSouthernCross Linkedin: https://www.linkedin.com/in/southerncross-ai-41b87a357/ Tiktok: https://www.tiktok.com/@southern.cross.ai Youtube: https://www.tiktok.com/@southern.cross.ai
7 | 1 | Write user stories | We decided to write user stories to better deconstruct the our product application. | Team meeting | All AmplifyAI Team Members | The AmplifyAI Team, Tutor/Examiner, Client | 2 | 2 | 2 | 14/03/2025 | 28/03/2025
8 | 1 | Write product vision | We decided to use the Moore's template to wirte the product vision, in order to better illustrate the design of our product. | Team meeting | All AmplifyAI Team Members | The AmplifyAI Team, Tutor/Examiner, Client | 2 | 2 | 2 | 14/03/2025 | 28/03/2025
9 | 2 | Learn website contents generation tools | As advised by the clients, we decided to take some time to learn the Jekyll and Adobe Express for content generation in the future development and consistant account operation. | Client meeting, Team meeting | All AmplifyAI Team Members | The AmplifyAI Team, Client | 2 | 3 | 2 | 14/03/2025 | 04/04/2025

## 24S2(Legacy)
Decision Log
ID | Decision | Description of decision and impact | Source | Owner | Stakeholders | Importance | Urgency | Status | Due Date | Record of decision made
[6 empty] | Relative Importance: 1-High, 2-Medium, 3-Low | Relative Urgency: 1-High, 2-Medium, 3-Low | Status of item: 1-Not started, 2-In progress, 3-Complete
1 | Create and Finish the Team Charter | We decided what parts the Team Charter would consist of, how to write each part, and how to divide the work. After each person completed their part, the Team Charter was merged, and the entire team reviewed, edited, and improved the Team Charter. | Team meeting | All The Guild Team 3 Members | The Guild Team 3, Shadow Team, Tutor/Examiner, Client | 2 | 1 | 3 | 02/08/2024 | Finished and signed url: https://drive.google.com/file/d/1RVnn-Bv0gFc-HtMmui6QbSA0mAnBZLR2/view
2 | Create and Finish the Statement of Work | We decided what parts the Statement of Work consisted of, how to write each part, and how to divide the work. After each person completed their part, the Statement of Work was merged, and the whole team reviewed, edited and improved the Statement of Work. Finally, the Statement of Work was provided to the Client for review and feedback. | Team meeting | All The Guild Team 3 Members | The Guild Team 3, Shadow Team, Tutor/Examiner, Client | 2 | 1 | 3 | 02/08/2024 | Finished and signed url: https://drive.google.com/file/d/1HMcsTFTJuijrZ26Cy2bHK_00gAsmhukt/view
3 | Clarify the Unreal Engine 5 learning plan and learning method from week 3 to week 6 | Through group meetings, we decided on the Unreal Engine 5 learning plan from the third week to the sixth week. At the same time, our team also unified the source of courses for learning Unreal Engine 5: unified learning through courses on Udemy. | Team meeting | All The Guild Team 3 Members | The Guild Team 3, Tutor/Examiner, Client | 1 | 3 | 3 | 01/09/2024 | Team members' levels of Unreal Engine 5 abilities are different.
4 | Discuss the division of work for the Game Design Document, especially the initial ideas for the combat system and the design and decisions of combat-related elements | After our discussion, we decided on the preliminary design ideas for the combat system. At the same time, we discussed and designed elements related to combat, such as heroes, enemies, resources, etc. Finally, we also decided on the division of labor for writing the Game Design Document. | Team meeting | All The Guild Team 3 Members | The Guild Team 3, Shadow Team, Tutor/Examiner, Client | 1 | 1 | 3 | 28/08/2024 | Discussion made and outcome is shown in decision #6
5 | Based on the client's feedback on Statement of Work, we decided to further modify and improve it to become Statement of Work v2.0 | The client's feedback on our Statement of Work is that it lacks a detailed description of the Combat System. In response to this feedback, we decided to add a Combat System section to the current Statement of Work and describe it in detail. After completion, we will send it to the client and ask if they agree to sign it. | Client meeting, Team meeting | All The Guild Team 3 Members | The Guild Team 3, Shadow Team, Tutor/Examiner, Client | 2 | 2 | 3 | 28/08/2024 | Modified and signed url: https://drive.google.com/file/d/1HMcsTFTJuijrZ26Cy2bHK_00gAsmhukt/view
6 | Content work division for Audit 2 | Each member is responsible for writing the introduction of two characters.Task assignment: Game Design Document and SoW Combat System: Wenzhao Zheng & Xinyi Chen Technical Design Document (Parts 2-4), weekly report and decision log : Xiangyu Bi Technical Design Document (Parts 5-6), reflection log and meeting record: Ke Wen Technical Design Document (Part 7) , weekly report and meeting record : Qi Ji Technical Design Document (Parts 8-9) and risk management : Xuefei Luan Technical Design Document (Parts 10-13): Yuetao Zhang | Team meeting | All The Guild Team 3 Members | The Guild Team 3, Shadow Team, Tutor/Examiner, Client | 1 | 2 | 3 | 28/08/2024 | Game Design Document url: https://docs.google.com/document/d/1pDh0HxPk1OP-WMMqO45bW_3a09MAwjBoOhCfyO_T3FU/edit?tab=t.0#heading=h.no89x0mfkeki Technical Design Document url: https://docs.google.com/document/d/1U98ECEYVIwgkyTHMMsgAF1KO8wiqAe_JZLUpA0MT4js/edit?tab=t.0#heading=h.cvpjb9jp1hdf
7 | Design, develop and test the first playable demo | We decided to design and develop a playable turn-based combat demo based on the given assets. The work allocation is as followed: Project management: Xiangyu Bi, Qi Ji Designing: Wenzhao Zheng, Xinyi Chen, Qi Ji Developing: Wenzhao Zheng, Xinyi Chen, Ke Wen, Yuetao Zhang, Xuefei Luan, Xiangyu Bi, Qi Ji QA/Testing: Ke Wen, Yuetao Zhang, Xuefei Luan | Team meeting | All The Guild Team 3 Members | The Guild Team 3, Client | 1 | 2 | 3 | 03/10/2024 | Demo url: https://gitlab.cecs.anu.edu.au/u7705888/guild-g3-combatsystem/-/tree/63e1d508a9b4305c6937001a820445796da56af1/New_Template_Enemy/TurnBasedTemp
8 | Reallocation of document editing work for maintaining regular update | We reallocation the administrative documents tasks, in order to balance the tasks for different individuals. The reallocation is as followed: Decision Log: Wenzhao Zheng Client Meeting Minute: Xuefei Luan Tutor Meeting Minute: Yuetao Zhang Team Meeting Minute: Xinyi Chen Reflection Log: Ke Wen | Team meeting | All The Guild Team 3 Members | The Guild Team 3, Shadow Team, Tutor/Examiner, Client | 3 | 2 | 3 | 01/09/2024 | Decision Log url: https://docs.google.com/document/d/1ZRpqR38XuJQR6W-YIkPV29ODdDSbH0sD8dr0z9Qsnm0/edit?tab=t.0#heading=h.x8jyxcpemec3 Client Meeting url: https://gitlab.cecs.anu.edu.au/u7705888/guild-g3-combatsystem/-/tree/main/docs/Meetings/Client%20Meeting?ref_type=heads Tutor Meeting Minute url: https://gitlab.cecs.anu.edu.au/u7705888/guild-g3-combatsystem/-/tree/main/docs/Meetings/Tutor%20Meeting?ref_type=heads Team Meeting Minute url: https://gitlab.cecs.anu.edu.au/u7705888/guild-g3-combatsystem/-/tree/main/docs/Meetings/Team%20Meeting?ref_type=heads Reflection Log url: https://gitlab.cecs.anu.edu.au/u7705888/guild-g3-combatsystem/-/tree/main/docs/Feedback%20Log?ref_type=heads
9 | Video, poster preparation for audit 3. | A video to demonstrate the playability and a poster to explain our project. The work allocation is as followed: Video: Yuetao Zhang Poster: Xuefei Luan Animation: Xinyi Chen Hero Skills: Wenzhao Zheng Enemy Design: Qi Ji UI: Xiangyu Bi, Ke Wen | Team meeting | All The Guild Team 3 Members | The Guild Team 3, Client, Tutor, Shadow Team | 1 | 2 | 3 | 03/10/2024 | Video shown on the Audit 3 presentation.
This Decision Log is a refined document based on the 24s2 decision log. The original one is a Word-based document can be found here: https://docs.google.com/document/d/1ZRpqR38XuJQR6W-YIkPV29ODdDSbH0sD8dr0z9Qsnm0/edit?tab=t.0#heading=h.x8jyxcpemec3